## Sheet1
SPRINT | DATE | TYPE | REQUESTED BY | CHANGE TYPE | CHANGE DESCRIPTION | REASON | STATUS
3 | 8.10.2017 | Scope | Team | Learner Module | Game Room Setup delay | Raspberry Pi burnt, and thus unable to obtain measurements of the robot's movement | In Progress
3 | 8.10.2017 | Scope | Team | Account Module | Change in website provider | Wix had supported a limited number of plugins, especially since e-commerce was a huge concern for the sponsor, we researched and realised WordPress would be the better option | Completed
5 | 30.10.17 | Scope | Sponsor | Shopping Module | Included Shopping Module into scope | Expound on the e-commerce aspect of the site, provide a platform for aspiring game providers resources to start their game designs | In Progress
7 | 07.12.17 | Scope | Team | Robotics Module | Extend Game Server to a separate server | Unable to connect to the robot directly through WordPress | Completed
7 | 10.12.17 | Project Management | Project Manager | UAT 2 | UAT 2 Delay | Booking gameslot on WordPress still in progress | Completed
9 | 27.12.17 | Scope | Team | Game Provider Module | Removed admin access option for game providers, and inserted form option | Game providers should not have direct access to the administrative pages (database etc.) and games should be streamlined by admins to ensure the credibility and reputation of the site | Completed