## Sheet1
Risk Type | Risk Event | Mitigation
Technical Risk | Integration of the separate servers | Team to research on technology and experience it to gain proficiency
Resource Risk | Unexpected hardware issues | Team to keep testing hardware functionalities to ensure that hardware is in good condition. Team to also have spare parts for hardware in case of any hardware breakdown
Project Management Risk | Having to adjust tasks and schedule based on wrong estimation or unexpected hardware issues | Team to spend more time on current tasks to get back on track or research more to resolve hardware issues
Client Management Risk | Finding a balance between the school requirements as well as sponsor requirements | Try to understand both points of view and compromise. Consult supervisor if issues cannot be resolved with sponsor to ensure that everyone is on the same page